## Sayfa1
Start Date 30/09/2024
Week |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Procedural Steps | Current State | 30 September 2024 | 7 October 2024 | 14 October 2024 | 21 October 2024 | 28 October 2024 | 4 November 2024 | 11 November 2024 | 18 November 2024 | 25 November 2024 | 2 December 2024 | 9 December 2024 | 16 December 2024 | 23 December 2024 | 30 December 2024 | 6 January 2024 | 13 January 2024
Team Setup | Completed | bar: 1 to 2
Project Proposal Form | Completed | bar: 2
Project Selection Form | Completed | bar: 2
Project Work Plan | Completed | bar: 3 to 4
Literature Review | Completed | bar: 4 to 6
Software Requirements Specification | Continuing | bar: 6 to 9
Project Webpage | Continuing | bar: 10 to 12
Software Design Description | Continuing | bar: 10 to 13
Project Report | Continuing | bar: 10 to 15
Presentation | Continuing | bar: 13 to 14